## Raw_Data
Task ID | Project Name | Department | Assigned To | Role | Priority | Task Category | Start Date | Due Date | Completion Date | Estimated Hours | Actual Hours | Remarks
T001 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-01 | 2026-01-05 | 2026-01-04 | 10 | 9 | On Time
T002 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-01-02 | 2026-01-06 | 2026-01-05 | 8 | 10 | Delayed
T003 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-01-03 | 2026-01-08 | 2026-01-06 | 12 | 7 | Ongoing
T004 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-01-04 | 2026-01-10 | 2026-01-07 | 6 | 0 | Pending
T005 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-01-05 | 2026-01-09 | 2026-01-08 | 5 | 5 | Done
T006 | App Development | IT | Kiran | Developer | High | Coding | 2026-01-06 | 2026-01-12 | 2026-01-09 | 15 | 7 | Ongoing
T007 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-01-07 | 2026-01-14 | 2026-01-10 | 7 | 0 | Pending
T008 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-01-08 | 2026-01-13 | 2026-01-11 | 6 | 6 | Done
T009 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-01-09 | 2026-01-15 | 2026-01-12 | 10 | 4 | Ongoing
T010 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-01-10 | 2026-01-16 | 2026-01-13 | 8 | 3 | Ongoing
T011 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-01-11 | 2026-01-17 | 2026-01-14 | 6 | 0 | Pending
T012 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-01-12 | 2026-01-18 | 2026-01-15 | 10 | 10 | Done
T013 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-01-13 | 2026-01-19 | 2026-01-16 | 7 | 4 | Ongoing
T014 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-01-14 | 2026-01-20 | 2026-01-17 | 5 | 0 | Pending
T015 | App Development | IT | Kiran | Developer | High | Testing | 2026-01-15 | 2026-01-21 | 2026-01-18 | 14 | 16 | Delayed
T016 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-01-16 | 2026-01-22 | 2026-01-19 | 6 | 3 | Ongoing
T017 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-01-17 | 2026-01-23 | 2026-01-20 | 5 | 5 | Done
T018 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-01-18 | 2026-01-24 | 2026-01-21 | 9 | 4 | Ongoing
T019 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-19 | 2026-01-25 | 2026-01-22 | 12 | 9 | Ongoing
T020 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-01-20 | 2026-01-26 | 2026-01-23 | 8 | 0 | Pending
T021 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-01-21 | 2026-01-27 | 2026-01-24 | 10 | 10 | Done
T022 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-01-22 | 2026-01-28 | 2026-01-25 | 6 | 2 | Ongoing
T023 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-01-23 | 2026-01-29 | 2026-01-26 | 7 | 9 | Delayed
T024 | App Development | IT | Kiran | Developer | High | Testing | 2026-01-24 | 2026-01-30 | 2026-01-27 | 13 | 7 | Ongoing
T025 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-01-25 | 2026-01-31 | 2026-01-28 | 6 | 0 | Pending
T026 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-01-26 | 2026-02-01 | 2026-01-29 | 5 | 5 | Done
T027 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-01-27 | 2026-02-02 | 2026-01-30 | 5 | 3 | Ongoing
T028 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-01-28 | 2026-02-03 | 2026-01-31 | 6 | 2 | Pending
T029 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-01-29 | 2026-02-04 | 2026-02-01 | 12 | 12 | Ongoing
T030 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-01-30 | 2026-02-05 | 2026-02-02 | 14 | 32 | Done
T031 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-31 | 2026-01-05 | 2026-02-03 | 5 | 5 | On Time
T032 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-02-01 | 2026-01-06 | 2026-02-04 | 3 | 4.4647 | Delayed
T033 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-02-02 | 2026-01-08 | 2026-02-05 | 15 | 22 | Ongoing
T034 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-02-03 | 2026-01-10 | 2026-02-06 | 5 | 3 | Pending
T035 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-02-04 | 2026-01-09 | 2026-02-07 | 12 | 15 | Done
T036 | App Development | IT | Kiran | Developer | High | Coding | 2026-02-05 | 2026-01-12 | 2026-02-08 | 6 | 6 | Ongoing
T037 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-02-06 | 2026-01-14 | 2026-02-09 | 5 | 9 | Pending
T038 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-02-07 | 2026-01-13 | 2026-02-10 | 8 | 8 | Done
T039 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-02-08 | 2026-01-15 | 2026-02-11 | 7.2766 | 4.2093 | Ongoing
T040 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-02-09 | 2026-01-16 | 2026-02-12 | 2 | 4.1728 | Ongoing
T041 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-02-10 | 2026-01-17 | 2026-02-13 | 3 | 5 | Pending
T042 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-02-11 | 2026-01-18 | 2026-02-14 | 5 | 2 | Done
T043 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-02-12 | 2026-01-19 | 2026-02-15 | 7.1138 | 0 | Ongoing
T044 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-02-13 | 2026-01-20 | 2026-02-16 | 8 | 4.0268 | Pending
T045 | App Development | IT | Kiran | Developer | High | Testing | 2026-02-14 | 2026-01-21 | 2026-02-17 | 9 | 12 | Delayed
T046 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-02-15 | 2026-01-22 | 2026-02-18 | 6.9916 | 14 | Ongoing
T047 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-02-16 | 2026-01-23 | 2026-02-19 | 3 | 2 | Done
T048 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-02-17 | 2026-01-24 | 2026-02-20 | 10 | 5 | Ongoing
T049 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-02-18 | 2026-01-25 | 2026-02-21 | 15 | 8 | Ongoing
T050 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-02-19 | 2026-01-26 | 2026-02-22 | 12 | 9 | Pending
T051 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-02-20 | 2026-01-27 | 2026-02-23 | 6.7881 | 3.7714 | Done
T052 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-02-21 | 2026-01-28 | 2026-02-24 | 6 | 5 | Ongoing
T053 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-02-22 | 2026-01-29 | 2026-02-25 | 8 | 7 | Delayed
T054 | App Development | IT | Kiran | Developer | High | Testing | 2026-02-23 | 2026-01-30 | 2026-02-26 | 9 | 0 | Ongoing
T055 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-02-24 | 2026-01-31 | 2026-02-27 | 20 | 12 | Pending
T056 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-02-25 | 2026-02-01 | 2026-02-28 | 12 | 12 | Done
T057 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-02-26 | 2026-02-02 | 2026-03-01 | 13 | 3 | Ongoing
T058 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-02-27 | 2026-02-03 | 2026-03-02 | 14 | 4 | Pending
T059 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-02-28 | 2026-02-04 | 2026-03-03 | 15 | 3.4796 | Ongoing
T060 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-03-01 | 2026-02-05 | 2026-03-04 | 6.4217 | 6 | Done
T061 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-03-02 | 2026-01-05 | 2026-03-05 | 7 | 10 | On Time
T062 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-03-03 | 2026-01-06 | 2026-03-06 | 8 | 11 | Delayed
T063 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-03-04 | 2026-01-08 | 2026-03-07 | 9 | 14 | Ongoing
T064 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-03-05 | 2026-01-10 | 2026-03-08 | 11 | 16 | Pending
T065 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-03-06 | 2026-01-09 | 2026-03-09 | 12 | 3.2607 | Done
T066 | App Development | IT | Kiran | Developer | High | Coding | 2026-03-07 | 2026-01-12 | 2026-03-10 | 1 | 3 | Ongoing
T067 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-03-08 | 2026-01-14 | 2026-03-11 | 12 | 7 | Pending
T068 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-03-09 | 2026-01-13 | 2026-03-12 | 6.096 | 8 | Done
T069 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-03-10 | 2026-01-15 | 2026-03-13 | 1 | 9 | Ongoing
T070 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-03-11 | 2026-01-16 | 2026-03-14 | 12 | 5 | Ongoing
T071 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-03-12 | 2026-01-17 | 2026-03-15 | 3 | 6 | Pending
T072 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-03-13 | 2026-01-18 | 2026-03-16 | 5.9331 | 7 | Done
T073 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-03-14 | 2026-01-19 | 2026-03-17 | 4 | 1 | Ongoing
T074 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-03-15 | 2026-01-20 | 2026-03-18 | 12 | 3 | Pending
T075 | App Development | IT | Kiran | Developer | High | Testing | 2026-03-16 | 2026-01-21 | 2026-03-19 | 1 | 2.8958 | Delayed
T076 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-03-17 | 2026-01-22 | 2026-03-20 | 12 | 4 | Ongoing
T077 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-03-18 | 2026-01-23 | 2026-03-21 | 1 | 5 | Done
T078 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-03-19 | 2026-01-24 | 2026-03-22 | 13 | 6 | Ongoing
T079 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-03-20 | 2026-01-25 | 2026-03-23 | 15 | 7 | Ongoing
T080 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-03-21 | 2026-01-26 | 2026-03-24 | 5.6074 | 8 | Pending
T081 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-03-22 | 2026-01-27 | 2026-03-25 | 17 | 9 | Done
T082 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-03-23 | 2026-01-28 | 2026-03-26 | 8 | 1 | Ongoing
T083 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-03-24 | 2026-01-29 | 2026-03-27 | 9 | 21 | Delayed
T084 | App Development | IT | Kiran | Developer | High | Testing | 2026-03-25 | 2026-01-30 | 2026-03-28 | 5.4446 | 2.5674 | Ongoing
T085 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-03-26 | 2026-01-31 | 2026-03-29 | 2 | 23 | Pending
T086 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-03-27 | 2026-02-01 | 2026-03-30 | 11 | 12 | Done
T087 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-03-28 | 2026-02-02 | 2026-03-31 | 13 | 11 | Ongoing
T088 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-03-29 | 2026-02-03 | 2026-04-01 | 12 | 10 | Pending
T089 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-03-30 | 2026-02-04 | 2026-04-02 | 11 | 2.385 | Ongoing
T090 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-03-31 | 2026-02-05 | 2026-04-03 | 12 | 3 | Done
T091 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-04-01 | 2026-01-05 | 2026-04-04 | 13 | 7 | On Time
T092 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-04-02 | 2026-01-06 | 2026-04-05 | 12 | 8 | Delayed
T093 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-04-03 | 2026-01-08 | 2026-04-06 | 15 | 9 | Ongoing
T094 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-04-04 | 2026-01-10 | 2026-04-07 | 3 | 4 | Pending
T095 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-04-05 | 2026-01-09 | 2026-04-08 | 6 | 5 | Done
T096 | App Development | IT | Kiran | Developer | High | Coding | 2026-04-06 | 2026-01-12 | 2026-04-09 | 4.956 | 6 | Ongoing
T097 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-04-07 | 2026-01-14 | 2026-04-10 | 7 | 8 | Pending
T098 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-04-08 | 2026-01-13 | 2026-04-11 | 8 | 1 | Done
T099 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-04-09 | 2026-01-15 | 2026-04-12 | 9 | 11 | Ongoing
T100 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-04-10 | 2026-01-16 | 2026-04-13 | 11 | 8 | Ongoing

## Cleaned_Data
Task ID | Project Name | Department | Assigned To | Role | Priority | Task Category | Start Date | Due Date | Completion Date | Estimated Hours | Actual Hours | Remarks
T001 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-01 | 2026-01-05 | 2026-01-04 | 10 | 9 | On Time
T002 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-01-02 | 2026-01-06 | 2026-01-05 | 8 | 10 | Delayed
T003 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-01-03 | 2026-01-08 | 2026-01-06 | 12 | 7 | Ongoing
T004 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-01-04 | 2026-01-10 | 2026-01-07 | 6 | 0 | Pending
T005 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-01-05 | 2026-01-09 | 2026-01-08 | 5 | 5 | Done
T006 | App Development | IT | Kiran | Developer | High | Coding | 2026-01-06 | 2026-01-12 | 2026-01-09 | 15 | 7 | Ongoing
T007 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-01-07 | 2026-01-14 | 2026-01-10 | 7 | 0 | Pending
T008 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-01-08 | 2026-01-13 | 2026-01-11 | 6 | 6 | Done
T009 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-01-09 | 2026-01-15 | 2026-01-12 | 10 | 4 | Ongoing
T010 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-01-10 | 2026-01-16 | 2026-01-13 | 8 | 3 | Ongoing
T011 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-01-11 | 2026-01-17 | 2026-01-14 | 6 | 0 | Pending
T012 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-01-12 | 2026-01-18 | 2026-01-15 | 10 | 10 | Done
T013 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-01-13 | 2026-01-19 | 2026-01-16 | 7 | 4 | Ongoing
T014 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-01-14 | 2026-01-20 | 2026-01-17 | 5 | 0 | Pending
T015 | App Development | IT | Kiran | Developer | High | Testing | 2026-01-15 | 2026-01-21 | 2026-01-18 | 14 | 16 | Delayed
T016 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-01-16 | 2026-01-22 | 2026-01-19 | 6 | 3 | Ongoing
T017 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-01-17 | 2026-01-23 | 2026-01-20 | 5 | 5 | Done
T018 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-01-18 | 2026-01-24 | 2026-01-21 | 9 | 4 | Ongoing
T019 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-19 | 2026-01-25 | 2026-01-22 | 12 | 9 | Ongoing
T020 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-01-20 | 2026-01-26 | 2026-01-23 | 8 | 0 | Pending
T021 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-01-21 | 2026-01-27 | 2026-01-24 | 10 | 10 | Done
T022 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-01-22 | 2026-01-28 | 2026-01-25 | 6 | 2 | Ongoing
T023 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-01-23 | 2026-01-29 | 2026-01-26 | 7 | 9 | Delayed
T024 | App Development | IT | Kiran | Developer | High | Testing | 2026-01-24 | 2026-01-30 | 2026-01-27 | 13 | 7 | Ongoing
T025 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-01-25 | 2026-01-31 | 2026-01-28 | 6 | 0 | Pending
T026 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-01-26 | 2026-02-01 | 2026-01-29 | 5 | 5 | Done
T027 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-01-27 | 2026-02-02 | 2026-01-30 | 5 | 3 | Ongoing
T028 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-01-28 | 2026-02-03 | 2026-01-31 | 6 | 2 | Pending
T029 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-01-29 | 2026-02-04 | 2026-02-01 | 12 | 12 | Ongoing
T030 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-01-30 | 2026-02-05 | 2026-02-02 | 14 | 32 | Done
T031 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-31 | 2026-01-05 | 2026-02-03 | 5 | 5 | On Time
T032 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-02-01 | 2026-01-06 | 2026-02-04 | 3 | 4.4647 | Delayed
T033 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-02-02 | 2026-01-08 | 2026-02-05 | 15 | 22 | Ongoing
T034 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-02-03 | 2026-01-10 | 2026-02-06 | 5 | 3 | Pending
T035 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-02-04 | 2026-01-09 | 2026-02-07 | 12 | 15 | Done
T036 | App Development | IT | Kiran | Developer | High | Coding | 2026-02-05 | 2026-01-12 | 2026-02-08 | 6 | 6 | Ongoing
T037 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-02-06 | 2026-01-14 | 2026-02-09 | 5 | 9 | Pending
T038 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-02-07 | 2026-01-13 | 2026-02-10 | 8 | 8 | Done
T039 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-02-08 | 2026-01-15 | 2026-02-11 | 7.2766 | 4.2093 | Ongoing
T040 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-02-09 | 2026-01-16 | 2026-02-12 | 2 | 4.1728 | Ongoing
T041 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-02-10 | 2026-01-17 | 2026-02-13 | 3 | 5 | Pending
T042 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-02-11 | 2026-01-18 | 2026-02-14 | 5 | 2 | Done
T043 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-02-12 | 2026-01-19 | 2026-02-15 | 7.1138 | 0 | Ongoing
T044 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-02-13 | 2026-01-20 | 2026-02-16 | 8 | 4.0268 | Pending
T045 | App Development | IT | Kiran | Developer | High | Testing | 2026-02-14 | 2026-01-21 | 2026-02-17 | 9 | 12 | Delayed
T046 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-02-15 | 2026-01-22 | 2026-02-18 | 6.9916 | 14 | Ongoing
T047 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-02-16 | 2026-01-23 | 2026-02-19 | 3 | 2 | Done
T048 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-02-17 | 2026-01-24 | 2026-02-20 | 10 | 5 | Ongoing
T049 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-02-18 | 2026-01-25 | 2026-02-21 | 15 | 8 | Ongoing
T050 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-02-19 | 2026-01-26 | 2026-02-22 | 12 | 9 | Pending
T051 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-02-20 | 2026-01-27 | 2026-02-23 | 6.7881 | 3.7714 | Done
T052 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-02-21 | 2026-01-28 | 2026-02-24 | 6 | 5 | Ongoing
T053 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-02-22 | 2026-01-29 | 2026-02-25 | 8 | 7 | Delayed
T054 | App Development | IT | Kiran | Developer | High | Testing | 2026-02-23 | 2026-01-30 | 2026-02-26 | 9 | 0 | Ongoing
T055 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-02-24 | 2026-01-31 | 2026-02-27 | 20 | 12 | Pending
T056 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-02-25 | 2026-02-01 | 2026-02-28 | 12 | 12 | Done
T057 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-02-26 | 2026-02-02 | 2026-03-01 | 13 | 3 | Ongoing
T058 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-02-27 | 2026-02-03 | 2026-03-02 | 14 | 4 | Pending
T059 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-02-28 | 2026-02-04 | 2026-03-03 | 15 | 3.4796 | Ongoing
T060 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-03-01 | 2026-02-05 | 2026-03-04 | 6.4217 | 6 | Done
T061 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-03-02 | 2026-01-05 | 2026-03-05 | 7 | 10 | On Time
T062 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-03-03 | 2026-01-06 | 2026-03-06 | 8 | 11 | Delayed
T063 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-03-04 | 2026-01-08 | 2026-03-07 | 9 | 14 | Ongoing
T064 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-03-05 | 2026-01-10 | 2026-03-08 | 11 | 16 | Pending
T065 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-03-06 | 2026-01-09 | 2026-03-09 | 12 | 3.2607 | Done
T066 | App Development | IT | Kiran | Developer | High | Coding | 2026-03-07 | 2026-01-12 | 2026-03-10 | 1 | 3 | Ongoing
T067 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-03-08 | 2026-01-14 | 2026-03-11 | 12 | 7 | Pending
T068 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-03-09 | 2026-01-13 | 2026-03-12 | 6.096 | 8 | Done
T069 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-03-10 | 2026-01-15 | 2026-03-13 | 1 | 9 | Ongoing
T070 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-03-11 | 2026-01-16 | 2026-03-14 | 12 | 5 | Ongoing
T071 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-03-12 | 2026-01-17 | 2026-03-15 | 3 | 6 | Pending
T072 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-03-13 | 2026-01-18 | 2026-03-16 | 5.9331 | 7 | Done
T073 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-03-14 | 2026-01-19 | 2026-03-17 | 4 | 1 | Ongoing
T074 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-03-15 | 2026-01-20 | 2026-03-18 | 12 | 3 | Pending
T075 | App Development | IT | Kiran | Developer | High | Testing | 2026-03-16 | 2026-01-21 | 2026-03-19 | 1 | 2.8958 | Delayed
T076 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-03-17 | 2026-01-22 | 2026-03-20 | 12 | 4 | Ongoing
T077 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-03-18 | 2026-01-23 | 2026-03-21 | 1 | 5 | Done
T078 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-03-19 | 2026-01-24 | 2026-03-22 | 13 | 6 | Ongoing
T079 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-03-20 | 2026-01-25 | 2026-03-23 | 15 | 7 | Ongoing
T080 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-03-21 | 2026-01-26 | 2026-03-24 | 5.6074 | 8 | Pending
T081 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-03-22 | 2026-01-27 | 2026-03-25 | 17 | 9 | Done
T082 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-03-23 | 2026-01-28 | 2026-03-26 | 8 | 1 | Ongoing
T083 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-03-24 | 2026-01-29 | 2026-03-27 | 9 | 21 | Delayed
T084 | App Development | IT | Kiran | Developer | High | Testing | 2026-03-25 | 2026-01-30 | 2026-03-28 | 5.4446 | 2.5674 | Ongoing
T085 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-03-26 | 2026-01-31 | 2026-03-29 | 2 | 23 | Pending
T086 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-03-27 | 2026-02-01 | 2026-03-30 | 11 | 12 | Done
T087 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-03-28 | 2026-02-02 | 2026-03-31 | 13 | 11 | Ongoing
T088 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-03-29 | 2026-02-03 | 2026-04-01 | 12 | 10 | Pending
T089 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-03-30 | 2026-02-04 | 2026-04-02 | 11 | 2.385 | Ongoing
T090 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-03-31 | 2026-02-05 | 2026-04-03 | 12 | 3 | Done
T091 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-04-01 | 2026-01-05 | 2026-04-04 | 13 | 7 | On Time
T092 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-04-02 | 2026-01-06 | 2026-04-05 | 12 | 8 | Delayed
T093 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-04-03 | 2026-01-08 | 2026-04-06 | 15 | 9 | Ongoing
T094 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-04-04 | 2026-01-10 | 2026-04-07 | 3 | 4 | Pending
T095 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-04-05 | 2026-01-09 | 2026-04-08 | 6 | 5 | Done
T096 | App Development | IT | Kiran | Developer | High | Coding | 2026-04-06 | 2026-01-12 | 2026-04-09 | 4.956 | 6 | Ongoing
T097 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-04-07 | 2026-01-14 | 2026-04-10 | 7 | 8 | Pending
T098 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-04-08 | 2026-01-13 | 2026-04-11 | 8 | 1 | Done
T099 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-04-09 | 2026-01-15 | 2026-04-12 | 9 | 11 | Ongoing
T100 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-04-10 | 2026-01-16 | 2026-04-13 | 11 | 8 | Ongoing

## Calculation
Task ID | Project Name | Department | Assigned To | Role | Priority | Task Category | Start Date | Due Date | Completion Date | Progress % | Estimated Hours | Actual Hours | Remarks | Variance | Task Status | Progress% | Delay | Days Taken | Over Due
T001 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-01 | 2026-01-05 | 2026-01-04 | ca | 10 | 9 | On Time | -1 | Completed | 100 | No | 3 | No
T002 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-01-02 | 2026-01-06 | 2026-01-05 | 100 | 8 | 10 | Delayed | 2 | Completed | 100 | No | 3 | No
T003 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-01-03 | 2026-01-08 | 2026-01-06 | 60 | 12 | 7 | Ongoing | -5 | Completed | 100 | No | 3 | No
T004 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-01-04 | 2026-01-10 | 2026-01-07 | 0 | 6 | 0 | Pending | -6 | Completed | 100 | No | 3 | No
T005 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-01-05 | 2026-01-09 | 2026-01-08 | 100 | 5 | 5 | Done | 0 | Completed | 100 | No | 3 | No
T006 | App Development | IT | Kiran | Developer | High | Coding | 2026-01-06 | 2026-01-12 | 2026-01-09 | 50 | 15 | 7 | Ongoing | -8 | Completed | 100 | No | 3 | No
T007 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-01-07 | 2026-01-14 | 2026-01-10 | 0 | 7 | 0 | Pending | -7 | Completed | 100 | No | 3 | No
T008 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-01-08 | 2026-01-13 | 2026-01-11 | 100 | 6 | 6 | Done | 0 | Completed | 100 | No | 3 | No
T009 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-01-09 | 2026-01-15 | 2026-01-12 | 40 | 10 | 4 | Ongoing | -6 | Completed | 100 | No | 3 | No
T010 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-01-10 | 2026-01-16 | 2026-01-13 | 30 | 8 | 3 | Ongoing | -5 | Completed | 100 | No | 3 | No
T011 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-01-11 | 2026-01-17 | 2026-01-14 | 0 | 6 | 0 | Pending | -6 | Completed | 100 | No | 3 | No
T012 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-01-12 | 2026-01-18 | 2026-01-15 | 100 | 10 | 10 | Done | 0 | Completed | 100 | No | 3 | No
T013 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-01-13 | 2026-01-19 | 2026-01-16 | 50 | 7 | 4 | Ongoing | -3 | Completed | 100 | No | 3 | No
T014 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-01-14 | 2026-01-20 | 2026-01-17 | 0 | 5 | 0 | Pending | -5 | Completed | 100 | No | 3 | No
T015 | App Development | IT | Kiran | Developer | High | Testing | 2026-01-15 | 2026-01-21 | 2026-01-18 | 100 | 14 | 16 | Delayed | 2 | Completed | 100 | No | 3 | No
T016 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-01-16 | 2026-01-22 | 2026-01-19 | 60 | 6 | 3 | Ongoing | -3 | Completed | 100 | No | 3 | No
T017 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-01-17 | 2026-01-23 | 2026-01-20 | 100 | 5 | 5 | Done | 0 | Completed | 100 | No | 3 | No
T018 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-01-18 | 2026-01-24 | 2026-01-21 | 45 | 9 | 4 | Ongoing | -5 | Completed | 100 | No | 3 | No
T019 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-19 | 2026-01-25 | 2026-01-22 | 70 | 12 | 9 | Ongoing | -3 | Completed | 100 | No | 3 | No
T020 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-01-20 | 2026-01-26 | 2026-01-23 | 0 | 8 | 0 | Pending | -8 | Completed | 100 | No | 3 | No
T021 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-01-21 | 2026-01-27 | 2026-01-24 | 100 | 10 | 10 | Done | 0 | Completed | 100 | No | 3 | No
T022 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-01-22 | 2026-01-28 | 2026-01-25 | 30 | 6 | 2 | Ongoing | -4 | Completed | 100 | No | 3 | No
T023 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-01-23 | 2026-01-29 | 2026-01-26 | 100 | 7 | 9 | Delayed | 2 | Completed | 100 | No | 3 | No
T024 | App Development | IT | Kiran | Developer | High | Testing | 2026-01-24 | 2026-01-30 | 2026-01-27 | 55 | 13 | 7 | Ongoing | -6 | Completed | 100 | No | 3 | No
T025 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-01-25 | 2026-01-31 | 2026-01-28 | 0 | 6 | 0 | Pending | -6 | Completed | 100 | No | 3 | No
T026 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-01-26 | 2026-02-01 | 2026-01-29 | 100 | 5 | 5 | Done | 0 | Completed | 100 | No | 3 | No
T027 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-01-27 | 2026-02-02 | 2026-01-30 | 40 | 5 | 3 | Ongoing | -2 | Completed | 100 | No | 3 | No
T028 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-01-28 | 2026-02-03 | 2026-01-31 | 0 | 6 | 2 | Pending | -4 | Completed | 100 | No | 3 | No
T029 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-01-29 | 2026-02-04 | 2026-02-01 | 60 | 12 | 12 | Ongoing | 0 | Completed | 100 | No | 3 | No
T030 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-01-30 | 2026-02-05 | 2026-02-02 | 100 | 14 | 32 | Done | 18 | Completed | 100 | No | 3 | No
T031 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-01-31 | 2026-01-05 | 2026-02-03 | 52.8506 | 5 | 5 | On Time | 0 | Delayed | 0 | Yes | 3 | Yes
T032 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-02-01 | 2026-01-06 | 2026-02-04 | 43 | 3 | 4.4647 | Delayed | 1.4647 | Delayed | 0 | Yes | 3 | Yes
T033 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-02-02 | 2026-01-08 | 2026-02-05 | 23 | 15 | 22 | Ongoing | 7 | Delayed | 0 | Yes | 3 | Yes
T034 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-02-03 | 2026-01-10 | 2026-02-06 | 100 | 5 | 3 | Pending | -2 | Delayed | 0 | Yes | 3 | Yes
T035 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-02-04 | 2026-01-09 | 2026-02-07 | 23 | 12 | 15 | Done | 3 | Delayed | 0 | Yes | 3 | Yes
T036 | App Development | IT | Kiran | Developer | High | Coding | 2026-02-05 | 2026-01-12 | 2026-02-08 | 45 | 6 | 6 | Ongoing | 0 | Delayed | 0 | Yes | 3 | Yes
T037 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-02-06 | 2026-01-14 | 2026-02-09 | 2 | 5 | 9 | Pending | 4 | Delayed | 0 | Yes | 3 | Yes
T038 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-02-07 | 2026-01-13 | 2026-02-10 | 89 | 8 | 8 | Done | 0 | Delayed | 0 | Yes | 3 | Yes
T039 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-02-08 | 2026-01-15 | 2026-02-11 | 77 | 7.2766 | 4.2093 | Ongoing | -3.0673 | Delayed | 0 | Yes | 3 | Yes
T040 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-02-09 | 2026-01-16 | 2026-02-12 | 6 | 2 | 4.1728 | Ongoing | 2.1728 | Delayed | 0 | Yes | 3 | Yes
T041 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-02-10 | 2026-01-17 | 2026-02-13 | 44 | 3 | 5 | Pending | 2 | Delayed | 0 | Yes | 3 | Yes
T042 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-02-11 | 2026-01-18 | 2026-02-14 | 2 | 5 | 2 | Done | -3 | Delayed | 0 | Yes | 3 | Yes
T043 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-02-12 | 2026-01-19 | 2026-02-15 | 12 | 7.1138 | 0 | Ongoing | -7.1138 | Delayed | 0 | Yes | 3 | Yes
T044 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-02-13 | 2026-01-20 | 2026-02-16 | 15 | 8 | 4.0268 | Pending | -3.9732 | Delayed | 0 | Yes | 3 | Yes
T045 | App Development | IT | Kiran | Developer | High | Testing | 2026-02-14 | 2026-01-21 | 2026-02-17 | 49.7049 | 9 | 12 | Delayed | 3 | Delayed | 0 | Yes | 3 | Yes
T046 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-02-15 | 2026-01-22 | 2026-02-18 | 34 | 6.9916 | 14 | Ongoing | 7.0084 | Delayed | 0 | Yes | 3 | Yes
T047 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-02-16 | 2026-01-23 | 2026-02-19 | 49.2555 | 3 | 2 | Done | -1 | Delayed | 0 | Yes | 3 | Yes
T048 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-02-17 | 2026-01-24 | 2026-02-20 | 67 | 10 | 5 | Ongoing | -5 | Delayed | 0 | Yes | 3 | Yes
T049 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-02-18 | 2026-01-25 | 2026-02-21 | 4 | 15 | 8 | Ongoing | -7 | Delayed | 0 | Yes | 3 | Yes
T050 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-02-19 | 2026-01-26 | 2026-02-22 | 77 | 12 | 9 | Pending | -3 | Delayed | 0 | Yes | 3 | Yes
T051 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-02-20 | 2026-01-27 | 2026-02-23 | 87 | 6.7881 | 3.7714 | Done | -3.0166 | Delayed | 0 | Yes | 3 | Yes
T052 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-02-21 | 2026-01-28 | 2026-02-24 | 88 | 6 | 5 | Ongoing | -1 | Delayed | 0 | Yes | 3 | Yes
T053 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-02-22 | 2026-01-29 | 2026-02-25 | 98 | 8 | 7 | Delayed | -1 | Delayed | 0 | Yes | 3 | Yes
T054 | App Development | IT | Kiran | Developer | High | Testing | 2026-02-23 | 2026-01-30 | 2026-02-26 | 76 | 9 | 0 | Ongoing | -9 | Delayed | 0 | Yes | 3 | Yes
T055 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-02-24 | 2026-01-31 | 2026-02-27 | 12 | 20 | 12 | Pending | -8 | Delayed | 0 | Yes | 3 | Yes
T056 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-02-25 | 2026-02-01 | 2026-02-28 | 47.2332 | 12 | 12 | Done | 0 | Delayed | 0 | Yes | 3 | Yes
T057 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-02-26 | 2026-02-02 | 2026-03-01 | 14 | 13 | 3 | Ongoing | -10 | Delayed | 0 | Yes | 3 | Yes
T058 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-02-27 | 2026-02-03 | 2026-03-02 | 46.7838 | 14 | 4 | Pending | -10 | Delayed | 0 | Yes | 3 | Yes
T059 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-02-28 | 2026-02-04 | 2026-03-03 | 15 | 15 | 3.4796 | Ongoing | -11.5204 | Delayed | 0 | Yes | 3 | Yes
T060 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-03-01 | 2026-02-05 | 2026-03-04 | 10 | 6.4217 | 6 | Done | -0.42165 | Delayed | 0 | Yes | 3 | Yes
T061 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-03-02 | 2026-01-05 | 2026-03-05 | 15 | 7 | 10 | On Time | 3 | Delayed | 0 | Yes | 3 | Yes
T062 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-03-03 | 2026-01-06 | 2026-03-06 | 45.8851 | 8 | 11 | Delayed | 3 | Delayed | 0 | Yes | 3 | Yes
T063 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-03-04 | 2026-01-08 | 2026-03-07 | 34 | 9 | 14 | Ongoing | 5 | Delayed | 0 | Yes | 3 | Yes
T064 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-03-05 | 2026-01-10 | 2026-03-08 | 43 | 11 | 16 | Pending | 5 | Delayed | 0 | Yes | 3 | Yes
T065 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-03-06 | 2026-01-09 | 2026-03-09 | 56 | 12 | 3.2607 | Done | -8.7393 | Delayed | 0 | Yes | 3 | Yes
T066 | App Development | IT | Kiran | Developer | High | Coding | 2026-03-07 | 2026-01-12 | 2026-03-10 | 76 | 1 | 3 | Ongoing | 2 | Delayed | 0 | Yes | 3 | Yes
T067 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-03-08 | 2026-01-14 | 2026-03-11 | 6 | 12 | 7 | Pending | -5 | Delayed | 0 | Yes | 3 | Yes
T068 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-03-09 | 2026-01-13 | 2026-03-12 | 76 | 6.096 | 8 | Done | 1.904 | Delayed | 0 | Yes | 3 | Yes
T069 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-03-10 | 2026-01-15 | 2026-03-13 | 88 | 1 | 9 | Ongoing | 8 | Delayed | 0 | Yes | 3 | Yes
T070 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-03-11 | 2026-01-16 | 2026-03-14 | 66 | 12 | 5 | Ongoing | -7 | Delayed | 0 | Yes | 3 | Yes
T071 | Website Revamp | IT | Sneha | Tester | Low | Testing | 2026-03-12 | 2026-01-17 | 2026-03-15 | 43.8628 | 3 | 6 | Pending | 3 | Delayed | 0 | Yes | 3 | Yes
T072 | Marketing Campaign | Marketing | Rahul | Analyst | High | Execution | 2026-03-13 | 2026-01-18 | 2026-03-16 | 32 | 5.9331 | 7 | Done | 1.0669 | Delayed | 0 | Yes | 3 | Yes
T073 | Hiring Drive | HR | Priya | Recruiter | Medium | Screening | 2026-03-14 | 2026-01-19 | 2026-03-17 | 24 | 4 | 1 | Ongoing | -3 | Delayed | 0 | Yes | 3 | Yes
T074 | Sales Report | Sales | Arjun | Executive | Low | Analysis | 2026-03-15 | 2026-01-20 | 2026-03-18 | 45 | 12 | 3 | Pending | -9 | Delayed | 0 | Yes | 3 | Yes
T075 | App Development | IT | Kiran | Developer | High | Testing | 2026-03-16 | 2026-01-21 | 2026-03-19 | 65 | 1 | 2.8958 | Delayed | 1.8958 | Delayed | 0 | Yes | 3 | Yes
T076 | Customer Survey | Marketing | Meena | Analyst | Medium | Data Entry | 2026-03-17 | 2026-01-22 | 2026-03-20 | 87 | 12 | 4 | Ongoing | -8 | Delayed | 0 | Yes | 3 | Yes
T077 | Payroll Update | HR | Anil | Manager | High | Verification | 2026-03-18 | 2026-01-23 | 2026-03-21 | 98 | 1 | 5 | Done | 4 | Delayed | 0 | Yes | 3 | Yes
T078 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-03-19 | 2026-01-24 | 2026-03-22 | 15 | 13 | 6 | Ongoing | -7 | Delayed | 0 | Yes | 3 | Yes
T079 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-03-20 | 2026-01-25 | 2026-03-23 | 17 | 15 | 7 | Ongoing | -8 | Delayed | 0 | Yes | 3 | Yes
T080 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-03-21 | 2026-01-26 | 2026-03-24 | 45 | 5.6074 | 8 | Pending | 2.3926 | Delayed | 0 | Yes | 3 | Yes
T081 | Marketing Campaign | Marketing | Rahul | Analyst | High | Design | 2026-03-22 | 2026-01-27 | 2026-03-25 | 90 | 17 | 9 | Done | -8 | Delayed | 0 | Yes | 3 | Yes
T082 | Hiring Drive | HR | Priya | Recruiter | Low | Interview | 2026-03-23 | 2026-01-28 | 2026-03-26 | 65 | 8 | 1 | Ongoing | -7 | Delayed | 0 | Yes | 3 | Yes
T083 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-03-24 | 2026-01-29 | 2026-03-27 | 0 | 9 | 21 | Delayed | 12 | Delayed | 0 | Yes | 3 | Yes
T084 | App Development | IT | Kiran | Developer | High | Testing | 2026-03-25 | 2026-01-30 | 2026-03-28 | 0 | 5.4446 | 2.5674 | Ongoing | -2.8771 | Delayed | 0 | Yes | 3 | Yes
T085 | Customer Survey | Marketing | Meena | Analyst | Medium | Analysis | 2026-03-26 | 2026-01-31 | 2026-03-29 | 9 | 2 | 23 | Pending | 21 | Delayed | 0 | Yes | 3 | Yes
T086 | Payroll Update | HR | Anil | Manager | High | Calculation | 2026-03-27 | 2026-02-01 | 2026-03-30 | 88 | 11 | 12 | Done | 1 | Delayed | 0 | Yes | 3 | Yes
T087 | Sales Target Plan | Sales | Divya | Manager | Medium | Execution | 2026-03-28 | 2026-02-02 | 2026-03-31 | 76 | 13 | 11 | Ongoing | -2 | Delayed | 0 | Yes | 3 | Yes
T088 | Website Revamp | IT | Ravi | Developer | Low | Bug Fix | 2026-03-29 | 2026-02-03 | 2026-04-01 | 100 | 12 | 10 | Pending | -2 | Delayed | 0 | Yes | 3 | Yes
T089 | Website Revamp | IT | Sneha | Tester | High | Testing | 2026-03-30 | 2026-02-04 | 2026-04-02 | 8 | 11 | 2.385 | Ongoing | -8.615 | Delayed | 0 | Yes | 3 | Yes
T090 | Marketing Campaign | Marketing | Rahul | Analyst | Medium | Planning | 2026-03-31 | 2026-02-05 | 2026-04-03 | 100 | 12 | 3 | Done | -9 | Delayed | 0 | Yes | 3 | Yes
T091 | Website Revamp | IT | Ravi | Developer | High | Development | 2026-04-01 | 2026-01-05 | 2026-04-04 | 99 | 13 | 7 | On Time | -6 | Delayed | 0 | Yes | 3 | Yes
T092 | Website Revamp | IT | Sneha | Tester | Medium | Testing | 2026-04-02 | 2026-01-06 | 2026-04-05 | 86 | 12 | 8 | Delayed | -4 | Delayed | 0 | Yes | 3 | Yes
T093 | Marketing Campaign | Marketing | Rahul | Analyst | High | Planning | 2026-04-03 | 2026-01-08 | 2026-04-06 | 38.9195 | 15 | 9 | Ongoing | -6 | Delayed | 0 | Yes | 3 | Yes
T094 | Hiring Drive | HR | Priya | Recruiter | Low | Recruitment | 2026-04-04 | 2026-01-10 | 2026-04-07 | 45 | 3 | 4 | Pending | 1 | Delayed | 0 | Yes | 3 | Yes
T095 | Sales Report | Sales | Arjun | Executive | High | Reporting | 2026-04-05 | 2026-01-09 | 2026-04-08 | 38.4702 | 6 | 5 | Done | -1 | Delayed | 0 | Yes | 3 | Yes
T096 | App Development | IT | Kiran | Developer | High | Coding | 2026-04-06 | 2026-01-12 | 2026-04-09 | 38.2455 | 4.956 | 6 | Ongoing | 1.044 | Delayed | 0 | Yes | 3 | Yes
T097 | Customer Survey | Marketing | Meena | Analyst | Medium | Research | 2026-04-07 | 2026-01-14 | 2026-04-10 | 6 | 7 | 8 | Pending | 1 | Delayed | 0 | Yes | 3 | Yes
T098 | Payroll Update | HR | Anil | Manager | High | Finance | 2026-04-08 | 2026-01-13 | 2026-04-11 | 98 | 8 | 1 | Done | -7 | Delayed | 0 | Yes | 3 | Yes
T099 | Sales Target Plan | Sales | Divya | Manager | High | Planning | 2026-04-09 | 2026-01-15 | 2026-04-12 | 45 | 9 | 11 | Ongoing | 2 | Delayed | 0 | Yes | 3 | Yes
T100 | Website Revamp | IT | Ravi | Developer | Medium | Bug Fix | 2026-04-10 | 2026-01-16 | 2026-04-13 | 66 | 11 | 8 | Ongoing | -3 | Delayed | 0 | Yes | 3 | Yes
Formulas:
Over Due = IF(AND(Calculation[[#This Row],[Task Status]]<>"Completed",TODAY()>Calculation[[#This Row],[Due Date]]),"Yes","No")

## KPI_Summary
KPI Summary | Values
Total Tasks | 101
Completed Tasks | 30
Pending Tasks | 0
Dalayed Tasks | 70
Tasks Completion | 0.29703
High Priority Task | 51
Average Completion Time | 3
Productivity Indicator | 0.29703

## Pivot_Table
Tasks by Status |  | Tasks by Department |  | Priority Distribution |  | Employee Performance
Task Status | Count of Task ID | Department | Count of Task ID | Priority | Count of Task ID | Task Status | (All)
Completed | 82 | HR | 20 | High | 51
Delayed | 10 | IT | 37 | Low | 16 | Assigned To | Count of Task ID
In progress | 8 | Marketing | 23 | Medium | 33 | Anil | 10
Grand Total | 100 | Sales | 20 | (blank) |  | Arjun | 10
|  | (blank) |  | Grand Total | 100 | Divya | 10
|  | Grand Total | 100 |  |  | Kiran | 10
[6 empty] | Meena | 10
Tasks Completion Trend |  | Project -Wise Progress |  | Delayed Tasks Analysis |  | Priya | 10
Row Labels | Count of Task ID | Project Name | Average of Progress % | Task Status | (All) | Rahul | 13
<04-01-2026 | 63 | App Development | 55.495 | Delay | (All) | Ravi | 14
Jan | 31 | Customer Survey | 21.6 |  |  | Sneha | 13
Feb | 6 | Hiring Drive | 45.7 | Assigned To | Count of Task ID | (blank)
Grand Total | 100 | Marketing Campaign | 59.763 | Anil | 10 | Grand Total | 100
|  | Payroll Update | 84.5489 | Arjun | 10
|  | Sales Report | 47.547 | Divya | 10
|  | Sales Target Plan | 50.7 | Kiran | 10
|  | Website Revamp | 43.8609 | Meena | 10
|  | (blank) |  | Priya | 10
|  | Grand Total | 50.2345 | Rahul | 13
|  |  |  | Ravi | 14
|  |  |  | Sneha | 13
(blank)
|  |  |  | Grand Total | 100

## Dashboard
Management and Task Tracking Dashboard
101
Total Tasks
30 Completed Tasks
51 High Priority Tasks
70
Delayed Tasks
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.